| Pre-Planning Responsibility | Assigned To | Hours to Complete | Dates/Details | Status |
| --- | --- | --- | --- | --- |
| Overall Planning |  |  |  |  |
| Create Planning Meetings with Partners | Bina | ~8 hours per person |  | In-Progress |
| Secure Classroom/Meeting Facilities | Brad | 1 hour |  | Complete |
| Hire Teacher and Coordinator | Brad | 6 hours |  | Complete |
| Create a Budget & Other Admin | Brad | 3 hours |  | To be Completed by Mid-May |
| MOU with city, district and County | Randy/Nancy/Darin |  | By Mid May |  |
| Student Recruitment/Selection |  |  |  |  |
| Create Pamphlet and Application | Randy |  | April 11th – 15th | In-Progress |
| Confirm plan to Recruit Students Randy/Lauren | Randy and Lauren |  | April 14th 1:30-2:30 | Scheduled |
| Distribute applications and flyers | Randy |  | April 18th RV, YCHS, Albert P. | Scheduled |
| Outreach to Principals and teachers(AVID esp and school counselors) to help with recruitment/Outreach to students | Nancy and Lauren |  | April 18-May 5th |  |
| Engage Youth Commission to help with recruitment and provide input into overall SACH plan(?) | Brad |  |  |  |
| Develop orientation agenda | Brad and Lauren(bina?) |  | Before May 5th |  |
| Hold Parent/Student Orientation | All |  | May 5th 6pm at City Hall | scheduled |
| Student Application Due |  |  | May 6th |  |
| Collection of Applications | Nancy |  | May 9th – electronic? |  |
| Create data base of applicants | Darin |  | May 10th |  |
| Set up student interviews- Coordinate with schools on location and times email students with time and date of their interview(Make calls, and emails) | Darin supported by Preet |  | May 10(coordinate with schools) May 11-12th call students, email students |  |
| Develop interview questions | Planning Team |  | Or before May 18th |  |
| Confirm interviews with panel(Locations, times, ) | Darin |  | May 11th |  |
| Copy applications for panel members and interview questions | Darin? |  | May 12th |  |
| Interview Student Candidates | Preet/Randy/Lauren |  | May 16th,17th,18th (1:30 -3:30) | Scheduled |
| Final student selections made | Luaren/Preet and Randy |  | May18th - after last interview? |  |
| Acceptance and wait list and rejection letters developed | Bina |  | May 10th |  |
| Acceptance and wait list letters sent to students vial email and also home to parents snail mail | Coordinator? |  | May 19th |  |
| Curriculum Design and Planning |  |  |  |  |
| Draft three week learning Objectives/ID Curriculum pieces | Bina/Lauren/Brad/?? |  | April 14th @ 2:30 – 3:30 |  |
| Approve learning objectives and curriculum | Partners |  | By May 1st |  |
| Develop curriculum | Bina, Lauren, Brad |  | By? |  |
| Prepare handouts and class materials for copying | Lauren |  |  |  |
| Design and Order T-Shirts | Coordinator/Lauren |  | June 1st 20 -25 Students | Design and Order T-Shirts |
| Speakers, Field Trips |  |  |  |  |
| Identify Speakers and Field Trips | Everyone |  | April 14th or next meeting |  |
| Contact Speakers to ask to speak | Coordinator |  | May 1st |  |
| Confirm speakers before presentation day | Coordinator |  |  |  |
| Arrange Logistics for Field Trips | Coordinator |  | May 1st |  |
| Job Shadows |  |  |  |  |
| Identify when job shadow orientation will be held and also dates and times of job shadows during the program, do you want to host a meet and greet with students day before job shadow starts during the program, determine how kids will get to job shadow | Brad and Lauren |  |  |  |
| Job Shadow- Invite to participate / create contact list | Darin |  | May 1st? |  |
| Job Shadows – confirm participation and invite to orientation | Darin |  | May 15th? |  |
| Job Shadow Orientation with Adults-plan agenda , develop handouts (adapt elk grove’s materials) | Darin, Lauren and Bina |  | Mid May |  |
| Hold Job Shadow orientation | Darin, Lauren, and? |  | End of May? May 31st |  |
| Poll students on interest and Match students with job shadows based on student interest | Lauren, and Coordinator |  | After program begins |  |
| Job shadow meet and greet with students |  |  | June 10th |  |
| Notify job shadows of name of students , date and time of pick up for job shadow noon-2pm on June 13th and 14th , 20th and 21st | Coordinator |  | A few days before job shadow |  |
| Pre-Planning Responsibility | Assigned To | Hours to Complete | Dates/Details | Status |
| Program Implementation Pre admin work |  |  |  |  |
| Create final List of Students and Info | Coordinator |  | By End of May Email Addresses, Emergency Contacts |  |
| Create overall schedule and itinerary | Coordinator consulting with Lauren/Planning team |  | End of May |  |
| Collect Field Trip Forms | Coordinator |  | June 6th |  |
| Copy Handouts and Arrange Materials | Coordinator |  |  |  |
| Coordinate Food Delivery | Coordinator |  |  |  |
| Arrange for T shirts | Coordinator |  |  |  |
| Write Thank You Notes | Coordinator |  | Speakers and Job Shadow Participants |  |
| Graduation Logistics | Coordinator/Teacher |  | Invitations, agenda, food, photos, speakers.. |  |
| Create a Social Media Presence | Coordinator |  | Websites, facebook, instagram….. |  |
| Create/Collect Evaluations | Coordinator/Bina |  | Evals from Students, Job Shadows….. |  |
| Observe ____ Classes per week | Bina |  | Support Teacher in flow, content, eval |  |
| Revise/Revamp Curriculum for 2017 | Teacher/Partners |  |  |  |
| Wrap Up Meeting with Partners | Partners |  | June 27th or June 28th |  |